## Worksheet 1
Phases and tasks | Observed challenged in relation to power and empowerment issues | Strategies used in response
TDR phase A: problem framing and team-building
NA task 1: preparing the process | The existing balance of power and socio-political dynamics could not be observed by the project team at the start of the process (there were neither time nor resources to conduct a thorough study prior to initiating the engagement in Kolkata) | Assure that the selected community is the best available project site through a careful selection process with selection criteria that include the community stakeholders' competence and willingness to engage
Pay continuous attention to socio-political dynamics and modify process designs when needed throughout the project duration
| Differences in existing community organization structures caused uneven representation of groups in the negotiation process (Khulna and Kolkata) | Observe and accept an uneven representation in the negotiation process as a limitation of the project Include the groups that are under-represented in research data collection and analysis to make interests and roles visible
| Large power distance existed between government decision-making and communities (Kolkata) | Use the research process and the participation of an international science team as leverage to engage with government decision-makers
NA task 2: reaching agreement on process design | The project team members were learning about (NA) process design and steps themselves | Ask for help from an internationally recognized local NA expert for the external facilitation of the first workshops
TDR phase B: Co-creation of solution-oriented, transferable knowledge
NA task 3: joint fact-finding and situation analysis (problem analysis) | The competence to articulate and share problem views was different among the stakeholders and project team members | Use visual methods for problem appraisal (e.g. social village maps) Develop a joint language through the establishment of a shared vocabulary and a list of terminology
Use of role-play games to share the analysis insights
Use of low-cost community testing kits
NA task 4: solutions analysis | Urgent problems demanded short-term visible results for the community stakeholders (Khulna and Kolkata), thus threatening their longer-term engagement in the TDR process | Free up project resources and mobilize additional resources to work on the emergent issues of immediate need in the villages (also if they were a less good fit for the research agenda of the project)
TDR phase C: reintegrating and applying the produced knowledge in both scientific and societal practice
NA task 5: Forging agreement | The deeper lying conflicts and issues could not be addressed within the project's limits | Focus on other significant issues for the community and in the research
| Some powerful actors did not engage (fully), making an agreement with them difficult | Ensure the participation of other actors with influence (mainly local government actors)
Mobilize media (Khulna)
NA task 6: communication with constituencies | Language barriers existed between (some of the) team members and communities; illiteracy levels were high among the local community members | Prepare specific stakeholder communication materials using translations and images
| Heterogeneity was large in the peri-urban community groups | Organize small-scale community meetings with different sub-groups (frequently)
NA task 7: monitoring agreed actions | The limited project time span, with the first agreements reached only after the initial years, made longer-term monitoring by project team members difficult | Monitor within the project time frame through continued periodic visits and workshops with community and government representatives
Establish a platform linked to other projects and initiatives with continued monitoring by local project partners (peri-urban water forum Khulna)
NA task 8: strengthening capacity of participants to become and remain equal partners in negotiations | Sustained capacity was threatened by short project time spans(and capacity strengthening challenges discussed with some of above tasks) | Link up to the existing structures for collective action and planning (village water council in Kolkata village)